## Ark1
Project Methodology Course Assignment
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | LAUNCH
Website Development for Lothus frukt og saft | [5 empty] | mon | tue | wed | thur | fri | mon | tue | wed | thur | fri | mon | tue | wed | thur | fri | mon | tue | wed | thur | fri | mon
Task | Assigned to | Duration | Start date | End Date | Status | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-28
Lofthus frukt og saft |  | 4 week | 2020-08-31 | 2020-09-28 | Active
Project Planning |  | 5 days | 2020-08-31 | 2020-09-07 | Upcoming | bar: WEEK 1 mon to WEEK 1 fri
Define requirements, goals & brainstorming | All team members | 2 days | 2020-08-31 | 2020-09-01 | bar: WEEK 1 mon to WEEK 1 tue
Research & Analyze competitors | Project manager | 1 day | 2020-09-02 | 2020-09-02 | bar: WEEK 1 wed
Strategic planning | Project manager | 1 day | 2020-09-03 | 2020-09-03 | bar: WEEK 1 thur
Content planning | Content developer | 1 day | 2020-09-03 | 2020-09-03 | bar: WEEK 1 thur
Meeting with clients | All team members | 1 day | 2020-09-04 | 2020-09-04 | bar: WEEK 1 fri
Design |  | 5 days | 2020-09-07 | 2020-09-14 | Upcoming | bar: WEEK 2 mon to WEEK 2 fri
Sitemap | Front-End Developer | 1 day | 2020-09-07 | 2020-09-07 | bar: WEEK 2 mon
Wireframe layout | Designer | 1 day | 2020-09-08 | 2020-09-08 | bar: WEEK 2 tue
Moodboard | Designer | 1 day | 2020-09-09 | 2020-09-09 | bar: WEEK 2 wed
Photoshoot of products and employees | Photographer | 1 day | 2020-09-09 | 2020-09-09 | bar: WEEK 2 wed
Prototype of design | Designer | 1 day | 2020-09-10 | 2020-09-10 | bar: WEEK 2 thur
Rewieving with client | All team members | 1 day | 2020-09-11 | 2020-09-11 | bar: WEEK 2 fri
Development |  | 5 days | 2020-09-07 | 2020-09-14 | Upcoming | bar: WEEK 3 mon to WEEK 3 fri
Content writing | Content developer | 2 days | 2020-09-14 | 2020-09-15 | bar: WEEK 3 mon to WEEK 3 tue
UX/UI Planning and testing | Designer | 2 days | 2020-09-15 | 2020-09-16 | bar: WEEK 3 tue to WEEK 3 wed
Coding, integration and site build | Front-End Developer | 4 days | 2020-09-14 | 2020-09-17 | bar: WEEK 3 mon to WEEK 3 thur
Client feedback meeting | All team members | 1 day | 2020-09-18 | 2020-09-18 | bar: WEEK 3 fri
Testing & Launch |  | 5 days | 2020-09-14 | 2020-09-21 | Upcoming | bar: WEEK 4 mon to WEEK 4 fri
Testing and document found issues | Front-End Developer | 1 day | 2020-09-21 | 2020-09-21 | bar: WEEK 4 mon
Correct issues found | Front-End Developer | 2 days | 2020-09-22 | 2020-09-23 | bar: WEEK 4 tue to WEEK 4 wed
Final Testing | Front-End Developer | 1 day | 2020-09-24 | 2020-09-24 | bar: WEEK 4 thur
Demo/Presentation with clients | All team members | 1 day | 2020-09-25 | 2020-09-25 | bar: WEEK 4 fri
Launch | All team members | 1 day | 2020-09-28 | 2020-09-28 | Upcoming | bar: LAUNCH mon
Team Member | [5 empty] | WEEK 1 tue: - Time for each phase
Project Manager | [5 empty] | WEEK 1 tue: - Time per task
Designer |  |  | T |  |  | WEEK 1 tue: - Meeting with clients
Content developer
Front-End Developer
Photographer